## Slide 1: Reflections on applying for TDAP and institutional designation
Haymo Thiel
Principal

## Slide 2: TDAP
Started process in autumn 2012
  Engaged a consultant
    Series of meetings with staff and students
    Reported to Board on potential to succeed
Visited QAA in February 2013
  Give notice of intent to apply
Compiled CSA Report
  Submitted to QAA in March 2014

## Slide 3: CSA
Comprehensive BIS Guidance (2004)
  Process
  Criteria informed structure of the CSA
    Superseded by BIS Guidance 2015
Produced a 78 page document
  Descriptive
  Critical/reflective
  Keyed in supporting evidence
    Hyperlinks (450)

## Slide 4: CSA
Introduction to application
  Institution, reasons for making application
Governance and academic management
  Board, management structures, financial sustainability, risk management
Academic standards and quality
  Regulatory framework
Student experience
  Resources, student support and progression
Academic staff
  Qualifications, scholarship and research
Summary of the case

## Slide 5: CSA
Appendices
  Student data
  Institutional structures and committees
  Preliminary preparations for TDAP
    Replacement costs
  Mapping document
  Letters of support

## Slide 6: Submission
Supporting evidence to CSA text
  Web
  Institution’s portal
  Designed the portal and keyed in at the end
CSA including appendices
Access to portal
Electronic submission to QAA

## Slide 7: Reflections
One person to write the CSA with a good knowledge of the institution
  Ownership
  Planning/structure
  Gather evidence but only works as one ‘story’
  Institutional not programmes
  Focus is on standards, quality and regulation/assurance
    Review against the QAA Quality Code
    We made use of QAA Institutional Review in 2012
Time and space
  12-15 month project
Drafts
  Keep to a minimum

## Slide 8: For the institution
Lots of communication to staff and students
  What is TDAP and why
  Progress along the way
Sense of the institution moving forward and achievement
Exciting and historic

## Slide 9: Scrutiny period
October 2014 to July 2015
Meetings based on academic calendar
Timetable
  Mid-point meeting
  Board of Governors, Management and Academic Committees, Periodic Review, Assessment Boards
  End- more detail on preparations for TDAP implementation

## Slide 10: Final stages
Draft scrutiny report
  September 2015
Report to ACDAP
  November 2015
Half day visit of the ACDAP Panel
  January 2016
ACDAP recommendation to QAA Board
  March 2016
QAA advice to BIS via HEFCE
  April 2016
Award made by Privy Council………

## Slide 11: Institutional designation
Began in September 2014
  Same time as scrutiny for TDAP began
Very little guidance
  Superseded by BIS Guidance 2015
HEFCE with focus on financial sustainability, data reporting, corporate governance and risk management
  HEFCE Memorandum of Assurance and Accountability

## Slide 12: Institutional designation
Finance department and Governors
  Relatively little input from academics
Training for governors
Set up an internal audit committee and implement systematic risk management procedures
Appoint internal auditors
Develop a student record system
Develop reporting systems (HESA)
Develop an estates strategy
Develop an Access Agreement

## Slide 13: Institutional designation
Met with HEFCE in February 2015
Submitted application to HEFCE in April 2015
Application 45 page document with extensive appendices
  No supporting evidence
  6 month project

## Slide 14: Institutional designation
Visits from HEFCE over summer 2015
Report of team to HEFCE Board
  September 2015
Letter from SoS (BIS)
  January 2016
Order of Designation laid
  Into force March 2016

## Slide 15: Reflections
Much shorter process than TDAP
  Designated before TDAP
Had less of a collegiate feel
TDAP application made ID application much easier
HEFCE review team over summer 2015
  Quiet period
  Respond quickly
  Fewer people involved

## Slide 16: Benefits
Matured as an HEI and part of the sector
  Change in outlook, accessibility to grants and potential for investment
  Cultural change for the whole institution
Look at our systems and processes
  Change and improve
Remained on good terms with our validating partner
  In process of separation and transition arrangements for students
    Mixed economy model
Feeling of progress and moving forward
  Looking beyond TDAP and designation (and name change)
We intend to admit students on our own degrees with direct HEFCE funding from September 2017
  5 years!